## Sheet1
Planned |  | December |  | January |  |  |  | February |  |  | March | Notes
Complete |  | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 24 | 3
Delay |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 20 | 21
| database design | [10 empty] | Completed ahead of time | bar: 11
| UI design | [10 empty] | Completed ahead of time | bar: 11
| infrastructure setup | [10 empty] | Completed ahead of time | bar: 11
| virtual environment setting | [10 empty] | Completed ahead of time | bar: 11
| index.html welcome message | [10 empty] | Completed ahead of time | bar: 11
| user / org registration | [10 empty] | Completed on time | bar: 12
| profile setup | [10 empty] | Completed on time | bar: 13
| admin page for org acceptance | [10 empty] | Completed on 07/01/25 | bar: 13
| event registration | [10 empty] | Enrollment done 14/01/25, not yet acceptance | bar: 14
| event enrollment / acceptance | [10 empty] | Completed 17/01/25 | bar: 14
| volunteer search for orgs | [10 empty] | Skipping implementation, will see if I can return | bar: 15
| event search for volunteers | [10 empty] | Completed on time | bar: 15
| event recommendation send | [10 empty] | Completed on time | bar: 16
| event chat + history | [10 empty] | Server side connection is more complex than expected. 03/02/2025 - breaktrhough, chat works, but no restriction yet Complete on 04/02/2025 | bar: 17
| unit testing | [10 empty] | Factory boy complete on 17/02/2025 | bar: 18
| user testing | [10 empty] | Last reply complete on 13/03/2025 | bar: 20
| bugfix | [10 empty] | No bugfix request from users, other fixes were implemented earlier. | bar: 21